## Agile Roadmap
BUILDORA WEBSITE BUILDER — AGILE PRODUCT ROADMAP 2026
V1 – MVP (Jan – Apr) |  |  |  | V1.1 (May) | V2 – Enhanced (Jun – Aug) |  |  | V3 – Intelligent Platform (Sep – Dec)
# | CATEGORY | FEATURE / MODULE | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | PRIORITY | STATUS
▌ AUTH & USER
1 |  | Signup / Login | ● | ● | [10 empty] | P0 | Done
2 |  | User Dashboard | ● | ● | [10 empty] | P0 | Done
3 |  | Project Mgmt (C/E/D) |  | ● | [10 empty] | P0 | Done
▌ PROJECT SYSTEM
4 |  | Project Name & Metadata |  | ● | [10 empty] | P0 | Done
5 |  | Subdomain Assignment |  | ● | ● | [9 empty] | P0 | Done
6 |  | Publish Status Tracking |  |  | ● | ● | [8 empty] | P0 | Done
▌ BUILDER INTERFACE
7 |  | Top Bar (Preview / Publish) |  | ● | ● | [9 empty] | P0 | Done
8 |  | Left Panel (Sections / Layouts) |  | ● | ● | [9 empty] | P0 | Done
9 |  | Canvas (Live Preview) |  |  | ● | ● | [8 empty] | P0 | Done
▌ SECTION BUILDER
10 |  | Navbar Section |  | ● | [10 empty] | P0 | Done
11 |  | Hero Section |  | ● | [10 empty] | P0 | Done
12 |  | Features Section |  | ● | ● | [9 empty] | P0 | Done
13 |  | About Section |  |  | ● | [9 empty] | P0 | Done
14 |  | Testimonials Section |  |  | ● | [9 empty] | P0 | Done
15 |  | Pricing Section |  |  | ● | [9 empty] | P0 | Done
16 |  | CTA Section |  |  | ● | [9 empty] | P0 | Done
17 |  | Footer Section |  |  | ● | [9 empty] | P0 | Done
▌ COMPONENT LIBRARY
18 |  | 4+ Layouts per Section |  | ● | ● | [9 empty] | P0 | Done
▌ CONTENT & STYLE
19 |  | Text Editing |  | ● | ● | [9 empty] | P0 | Done
20 |  | Image Upload |  |  | ● | [9 empty] | P0 | Done
21 |  | Icons & Links |  |  | ● | [9 empty] | P1 | Done
22 |  | Colors (Primary / Secondary) |  |  | ● | ● | [8 empty] | P0 | Done
23 |  | Fonts & Backgrounds |  |  | ● | ● | [8 empty] | P0 | Done
24 |  | Spacing & Alignment |  |  |  | ● | [8 empty] | P1 | Done
▌ TEMPLATES
25 |  | Startup Landing Page |  |  | ● | ● | [8 empty] | P0 | Done
26 |  | Consulting Website |  |  | ● | ● | [8 empty] | P0 | Done
27 |  | Portfolio Template |  |  |  | ● | [8 empty] | P1 | Done
▌ PREVIEW & PUBLISHING
28 |  | Desktop Preview |  |  |  | ● | [8 empty] | P0 | Done
29 |  | Mobile Preview |  |  |  | ● | [8 empty] | P0 | Done
30 |  | Static Build Generation |  |  |  | ● | [8 empty] | P0 | Done
31 |  | Deployment Pipeline |  |  |  | ● | [8 empty] | P0 | Done
32 |  | Live URL (Subdomain) |  |  |  | ● | [8 empty] | P0 | In Progress
▌ ADMIN PANEL
33 |  | Dashboard Stats |  |  | ● | ● | [8 empty] | P0 | Done
34 |  | User Management |  |  | ● | ● | [8 empty] | P0 | Done
35 |  | Website Management |  |  |  | ● | [8 empty] | P0 | Done
36 |  | Template Management |  |  |  | ● | [8 empty] | P1 | Done
37 |  | Deployment Monitoring |  |  |  | ● | [8 empty] | P1 | In Progress
▌ V1.1 — STABILIZATION & QA (May)
38 |  | End-to-End QA & Bug Fixes |  |  |  |  | ● | [7 empty] | P0 | In Progress
39 |  | Performance Optimization |  |  |  |  | ● | [7 empty] | P0 | In Progress
40 |  | Cross-browser / Responsive Fixes |  |  |  |  | ● | [7 empty] | P0 | In Progress
41 |  | Security & Auth Hardening |  |  |  |  | ● | [7 empty] | P0 | In Progress
▌ V2 — DRAG & DROP & ADVANCED STYLING (Jun–Aug)
42 |  | Drag-and-Drop Section Reordering | [5 empty] | ● | ● | [5 empty] | P0 | Planned
43 |  | Component Drag within Section | [6 empty] | ● | [5 empty] | P0 | Planned
44 |  | Animations & Transitions | [5 empty] | ● | ● | [5 empty] | P1 | Planned
45 |  | Advanced Color & Gradient Editor | [5 empty] | ● | [6 empty] | P1 | Planned
46 |  | Custom CSS Overrides | [6 empty] | ● | ● |  |  |  |  | P2 | Planned
47 |  | Responsive Breakpoint Controls | [7 empty] | ● |  |  |  |  | P1 | Planned
48 |  | V2 QA & Performance Testing | [7 empty] | ● |  |  |  |  | P0 | Planned
▌ V3 — AI, MARKETPLACE & COLLABORATION (Sep–Dec)
49 |  | AI Website Generation (prompt-to-site) | [8 empty] | ● | ● |  |  | P0 | Planned
50 |  | AI Section Copy Generator | [8 empty] | ● |  |  |  | P1 | Planned
51 |  | AI Image Suggestions | [9 empty] | ● |  |  | P2 | Planned
52 |  | Template Marketplace (buy/sell) | [9 empty] | ● | ● |  | P1 | Planned
53 |  | Creator Submission & Review Flow | [10 empty] | ● |  | P2 | Planned
54 |  | Custom Domain Mapping | [8 empty] | ● | ● |  |  | P0 | Planned
55 |  | SSL Auto-Provisioning | [9 empty] | ● |  |  | P0 | Planned
56 |  | CMS / Blog Module | [9 empty] | ● | ● |  | P1 | Planned
57 |  | Dynamic Pages & Collections | [10 empty] | ● |  | P2 | Planned
58 |  | Team Workspaces & Roles | [10 empty] | ● | ● | P1 | Planned
59 |  | Real-time Co-editing | [11 empty] | ● | P2 | Planned
60 |  | CDN & Edge Deployment | [10 empty] | ● | ● | P1 | Planned
61 |  | V3 Final QA & Load Testing | [11 empty] | ● | P0 | Planned

## Sprint Plan
Sprint | Sprint Name | Dates | Epic | User Story | Acceptance Criteria | Story Points | Assignee | Status
S1 | Core Auth & Dashboard | Jan 1–14 | Auth & User | As a user, I can sign up and log in securely | - Email/password auth - JWT session - Error states handled | 5 | Dev Team | Done
S1 | Core Auth & Dashboard | Jan 1–14 | Auth & User | As a user, I can view my dashboard with all projects | - Project list displayed - Empty state shown - Quick actions visible | 3 | Dev Team | Done
S2 | Project Setup & Builder Shell | Jan 15–28 | Project System | As a user, I can create a new website project with a name and subdomain | - Form validation - Subdomain uniqueness check - Project saved to DB | 5 | Dev Team | Done
S2 | Project Setup & Builder Shell | Jan 15–28 | Builder UI | As a user, I can open the builder and see the top bar and left panel | - Top bar renders - Left panel shows sections - No console errors | 5 | Dev Team | Done
S3 | Section Builder (Navbar, Hero, Features) | Feb 1–14 | Section Builder | As a user, I can add a Navbar section and select from 4 layouts | - 4 Navbar layouts available - Layout switches without refresh - Content preserved on switch | 8 | Dev Team | Done
S3 | Section Builder (Navbar, Hero, Features) | Feb 1–14 | Section Builder | As a user, I can configure a Hero section with heading and CTA button | - Text editable - CTA link configurable - Preview updates live | 8 | Dev Team | Done
S4 | Sections 4–8 + Content Edit | Feb 15–28 | Section Builder | As a user, I can add About, Testimonials, Pricing, CTA, and Footer sections | - All 5 sections render - 4 layouts each - Section order maintained | 13 | Dev Team | Done
S4 | Sections 4–8 + Content Edit | Feb 15–28 | Content | As a user, I can edit text, upload images, and set links in any section | - Text inline edit - Image upload to CDN - Link field saves | 8 | Dev Team | Done
S5 | Styling & Templates | Mar 1–14 | Style | As a user, I can change primary color, font, and background globally | - Color picker functional - Font family dropdown works - Changes apply instantly | 5 | Dev Team | Done
S5 | Styling & Templates | Mar 1–14 | Templates | As a user, I can select a starter template on project creation | - 3 templates available - Template loads pre-filled sections - Can be edited freely after | 8 | Dev Team | Done
S6 | Preview & Publishing | Mar 15–28 | Preview | As a user, I can preview my website in desktop and mobile views | - Responsive frame toggle - Preview loads in <3s - Reflects latest saved state | 5 | Dev Team | Done
S6 | Preview & Publishing | Mar 15–28 | Publishing | As a user, I can publish my website and get a live subdomain URL | - Static build generated - Deployed to CDN - URL active within 60s | 13 | Dev Team | Done
S7 | Admin Panel | Apr 1–14 | Admin | As an admin, I can view platform stats (users, sites, published) | - Dashboard with 5 KPI cards - Data updates in real-time - Recent activity log shown | 5 | Admin Dev | Done
S7 | Admin Panel | Apr 1–14 | Admin | As an admin, I can manage users (view, block, delete) | - User list with search - Block/unblock toggle - Delete with confirmation | 8 | Admin Dev | Done
S8 | Admin: Website & Template Mgmt | Apr 15–30 | Admin | As an admin, I can view all websites and manage deployments | - All sites visible - Publish status shown - Can delete any site | 5 | Admin Dev | Done
S8 | Admin: Website & Template Mgmt | Apr 15–30 | Admin | As an admin, I can add, edit, enable/disable templates | - Template CRUD works - Enable/disable toggle - Templates appear in builder | 5 | Admin Dev | Done
S9 (V1.1) | QA & Stabilization | May 1–31 | QA | As a QA engineer, I run end-to-end test suite covering all V1 flows | - All core flows pass - No P0 bugs open - Regression suite automated | 13 | QA Team | In Progress
S9 (V1.1) | QA & Stabilization | May 1–31 | QA | As a user, the platform performs well across Chrome, Firefox, Safari | - LCP < 2.5s - No layout breaks on mobile - Auth works in all browsers | 8 | QA Team | In Progress
S10 (V2) | Drag & Drop Builder | Jun 1–14 | D&D | As a user, I can drag sections up/down to reorder my page | - Drag handle on each section - Order persists on save - Undo available | 13 | Dev Team | Planned
S10 (V2) | Drag & Drop Builder | Jun 1–14 | D&D | As a user, I can drag components within a section | - Component drag active - Drop zones highlight - Layout updates correctly | 13 | Dev Team | Planned

## Product Backlog
ID | Epic | User Story | Priority | Version | Story Points | MoSCoW | Notes
US-001 | Auth | As a user, I can sign up with email and password | P0 | V1 | 5 | Must Have | JWT + bcrypt auth
US-002 | Auth | As a user, I can log in and see my dashboard | P0 | V1 | 3 | Must Have | Session persists 7 days
US-003 | Project | As a user, I can create a project with name and subdomain | P0 | V1 | 5 | Must Have | Subdomain uniqueness enforced
US-004 | Project | As a user, I can edit and delete my projects | P0 | V1 | 3 | Must Have | Soft delete
US-005 | Builder | As a user, I see the builder with top bar, left panel, canvas | P0 | V1 | 5 | Must Have | 3-panel layout
US-006 | Section | As a user, I can add a Navbar and choose from 4 layouts | P0 | V1 | 8 | Must Have
US-007 | Section | As a user, I can add a Hero section with text and CTA | P0 | V1 | 8 | Must Have
US-008 | Section | As a user, I can add Features, About, Testimonials sections | P0 | V1 | 8 | Must Have
US-009 | Section | As a user, I can add Pricing, CTA, Footer sections | P0 | V1 | 8 | Must Have
US-010 | Component | As a user, I can select from 4+ layouts per section | P0 | V1 | 5 | Must Have | Min 32 layout variants
US-011 | Content | As a user, I can edit headings, paragraphs, button labels | P0 | V1 | 5 | Must Have | Inline editing
US-012 | Content | As a user, I can upload images for any section | P0 | V1 | 5 | Must Have | CDN storage
US-013 | Content | As a user, I can set nav links and button URLs | P1 | V1 | 3 | Should Have | External + internal
US-014 | Style | As a user, I can change global primary/secondary colors | P0 | V1 | 3 | Must Have | Color picker
US-015 | Style | As a user, I can change font family and background | P0 | V1 | 3 | Must Have | 5 font families
US-016 | Style | As a user, I can adjust section padding and alignment | P1 | V1 | 3 | Should Have
US-017 | Template | As a user, I can start from a Startup Landing Page template | P0 | V1 | 5 | Must Have
US-018 | Template | As a user, I can start from a Consulting Website template | P0 | V1 | 5 | Must Have
US-019 | Template | As a user, I can start from a Portfolio template | P1 | V1 | 3 | Should Have
US-020 | Preview | As a user, I can preview in desktop and mobile views | P0 | V1 | 5 | Must Have | Responsive iframe
US-021 | Publish | As a user, I can publish and get a live subdomain URL | P0 | V1 | 13 | Must Have | Static site on CDN
US-022 | Admin | As an admin, I can view platform stats on dashboard | P0 | V1 | 5 | Must Have
US-023 | Admin | As an admin, I can manage users (view/block/delete) | P0 | V1 | 8 | Must Have
US-024 | Admin | As an admin, I can view and delete any website | P0 | V1 | 5 | Must Have
US-025 | Admin | As an admin, I can add/edit/disable templates | P1 | V1 | 5 | Should Have
US-026 | Admin | As an admin, I can view deployment logs | P1 | V1 | 3 | Should Have
US-027 | D&D | As a user, I can drag sections to reorder my page | P0 | V2 | 13 | Must Have | V2 feature
US-028 | D&D | As a user, I can drag components within sections | P0 | V2 | 13 | Must Have | V2 feature
US-029 | Style | As a user, I can add animations to sections | P1 | V2 | 8 | Should Have | CSS transitions
US-030 | Style | As a user, I can use gradient editor for backgrounds | P1 | V2 | 5 | Should Have
US-031 | Style | As a user, I can write custom CSS overrides | P2 | V2 | 8 | Could Have | Power user feature
US-032 | AI | As a user, I can generate a website from a text prompt | P0 | V3 | 21 | Must Have | GPT/Claude API
US-033 | AI | As a user, AI can write section copy for me | P1 | V3 | 13 | Should Have
US-034 | AI | As a user, AI suggests relevant stock images | P2 | V3 | 8 | Could Have
US-035 | Domains | As a user, I can connect a custom domain to my site | P0 | V3 | 13 | Must Have | DNS CNAME + SSL
US-036 | CMS | As a user, I can create a blog with posts | P1 | V3 | 21 | Should Have
US-037 | Collab | As a user, I can invite teammates to edit my project | P1 | V3 | 13 | Should Have | Role-based
US-038 | Marketplace | As a creator, I can sell my templates on a marketplace | P2 | V3 | 13 | Could Have | Revenue share model