## Roadmap
Website Builder – Product Roadmap
Features / Timeline | January | February | March | April | May | June | July | August | September | October | November | December
Auth – Login / Signup | bar: January to May
Auth – User Profile
Site Creation – Project Setup | bar: January to May
Site Creation – Template Selection
Editor UI – Section Builder | bar: January to May
Editor UI – Component Library
Editor UI – Content Customization | bar: January to May
Editor UI – Style Customization | January: Version V1: MVP – Core Website Builder
Preview System – Desktop
Preview System – Mobile
Preview Generation – Static Build | bar: January to May
Publishing System – Deploy
Storage – CDN | bar: January to May
Admin Panel – Dashboard
Admin Panel – User Management | bar: January to May
Admin Panel – Website Management
Site Creation – Project Setup | bar: April to September
Editor UI – Section Builder | April: V1.1: Testing & Bug Fixes
Editor UI – Component Library | bar: May to September
Drag & Drop – Section Reordering
Drag & Drop – Component Placement | bar: May to September
Responsive Layouts – Breakpoints
Responsive Layouts – Mobile First | May: Version V2: Drag & Drop, Themes, Responsive & Image Uploads
Image Uploads – Media Library | bar: January to April; October to December
Image Uploads – CDN Delivery | bar: May to September
Themes – Global Styles
Themes – Custom Palettes | bar: May to September
Preview System – Real-time
Preview Generation – On Demand | bar: May to September
Version History – Snapshot Save | bar: September to November
Version History – Restore Points
Themes – Marketplace | bar: September to November
Drag & Drop – Advanced
Responsive Layouts – Advanced | bar: September to November
Image Uploads – AI Optimization | September: Version V3: Version History, AI Generation & Advanced Features
Custom Domain Support
Team Collaboration
AI Website Generation | bar: September to November
CMS / Blogging
Ecommerce Support | bar: September to November
Version History – Final QA | bar: November to December
Performance Testing | November: V3.1: Final QA & Bug Fixes
Final Bug Fixing